## New Installation
PACS服务器安装路径
Hospital Name | Initial tester | Approver
Operation System | Passed |  | Failed
1. Windows 激活
2. Windows 升级
3. Windows 防火墙关闭
4. 关闭EP. /noexecute=AlwaysOff in boot.ini
5. 性能选项改为最佳性能
6. Processor scheduling is set to 'Background services'
7. Memory usage is set to 'System cache'
8. Error reporting is disabled but notify
9. Uncheck 'Automatically restart' in system failure
10. Write debugging information is set to Kernal memory dump
11. spectra/spclient user accounts are created
12. Set spectra as a member of Administrators
Utility on the server | Passsed |  | Failed
1. ESET NOD32 for trial (Anti-virus)
2. Notepad
3. Alzip
4. Benthic Golden and PLEdit
5. UltraVNC
Oracle 10g | Passed |  | Failed
1. The lastest patch 10.2.0.4 is installed
2. Check listener.ora file
3. Check tnsname.ora file
4. Schedule for Hot Backup at every night (Use Backup AZMA)
5. Schedule for Full Export once a week (Use Backup AZMA)
Oracle 11g | Passed |  | Failed
1. Check size of listener.log file in \\app\Administrator\diag\tnslsnr\<hostname>\listener\trace
2. Check listener.ora file
3. Check tnsname.ora file
4. Schedule for Hot Backup at every night (Use Backup AZMA)
5. Schedule for Full Export once a week (Use Backup AZMA)
IIS installation | Passed |  | Failed
1. Application Development
1-1. ASP.NET
1-2. .NET Extensibility
1-3. ASP
1-4. CGI
1-5. ISAPI Extensions
1-6. ISAPI Filters
1-7. Server Side Includes
2. Security
2-1. Basic Authentication
2-2. Windows Authentication
3. Management Tools
3-1. IIS Management Console
3-2. IIS Management Scripts and Tools
3-3. Management Service
3-4. IIS 6 Management Compatibility
3-4-1. IIS 6 Metabase Compatibility
3-4-2. IIS 6 WMI Compatibility
3-4-3. IIS 6 Scripting Tools
3-4-4. IIS 6 Management Console
4. FTP Publishing Service
4-1. FTP Server
4-2. FTP Management Console
5. .NET Framework Version 1.1
5-1. .NET Framework 1.1 Service Pack 1
5-2. .NET Framework 1.1 Service Pack 1 ASP.NET Security Update
5. iewebcontrol.msi
IIS configuration | Passed |  | Failed
1. Allow ASP.NET v1.1.4332 in ISAPI and CGI Restrictions
2. Create the MIME types ARC, DCM, DIC, MP3
3. Enable 32-bit Applications value is True in [Application Pools]-[Advanced Settings] (For 64bit)
4. Set Application Pool is ASP.NET 1.1 in [Default Web Site]-[Advanced Settings]
5. Add Virtual Directory of Volume in Default Web Site
INFINITT Admin UI | Value
1. Logo title
2. Base URL
3. License Type
4. Installation folder for WebView
Internet Security | Passed |  | Failed
1. Turn off Configure IE ESC
2. Internet Options
2-1. Changed security levels
2-2. Add IP Address in Trusted Sites
Admin Web page | Passed |  | Failed
1. Basic Code
1-1 Create the Institution code
1-2 Register all Netgates into Station
2. System
2-1. Profile - [Audit]
ENABLE_AUDIT_TRAIL : T
2-2. Profile - [Compatible]
FULL_TEXT_SEARCH : F
USE_V4_SCHEMA : F
2-3. Profile - [Netgate]
BACKUP_B1 : F
2-4. Profile - [Orthoview]
ENABLE : F
2-5. Profile - [Pantheon]
REMOTE_READING_CENTER : delete the default value
USE_REMOTE_READING : F
2-6. Profile - [Report]
ORDERED_ONLY : F
2-7. Profile - [Ruleset]
USE_ROUTERULE : F
USE_VERIFYRULE : F
2-8. Profile - [Server]
INTERNAL_IP_FILTER : set the xml properly then reimport
2-9. Profile - [Storage]
USE_J2K_COMPRESSION : T
2-10. Profile - [Validate]
ENABLE_STANDALONE_PACS : F
ENABLE_STANDALONE_RIS : F
USE_AUTOMATCH_RULE3 : F
2-11. Profile - [Worklist]
USE_DEMO_FOLDER : F
USE_REMOTE_COLLABORATION : F
2-12. User Defined UI Defaults
Make sure the UI is opened without error. If you get an error 'Server Error in '/' Application', please install iewebcontrol.msi
3. User
3-1. Make sure every user account has the institution code
3-2. Make sure all user levels are properly assigned into License manager
Final Testing | Passed |  | Failed
1. Start Negate service
2. Send bunch of studies to Netgate
3. Check Netgate log and Error folder
4. Login as admin and superadmin
5. Install WebView folder
6. Install Viewer folder
7. Create one test account
8. Login as you created on step 4
9. Open a study
10. Close a study
11. Test local burning

## Upgrade (hidden)
Check List for the Upgarde
Hospital Name | Upgrader | Approver
SPECTRA DATABASE | Value
1. Current version of spectra databse
2. New version
From 3090 to 30113 | Passed | Failed
ALTER TABLE LICENSESESSION DROP CONSTRAINT LICENSESSION_SESSION_TYPE_CK;
ALTER TABLE STUDYICON DROP CONSTRAINT STUDY_ICON_LOB_NN;
DELETE LICENSESESSION;
COMMIT;
@Patch_3090-3091.sql
@Patch_3091-30101.sql
@Patch_30101-30102.sql
@Patch_30102-30110.sql
@Patch_30110-30111.sql
@Patch_30111-30112.sql
@Patch_30112-30113.sql
@Spectrarebuild.sql
@Pkgmedia.sql
@Pbdmedia.sql
SELECT OBJECT_NAME FROM USER_OBJECTS WHERE STATUS != 'VALID'; (The result must be the "Found 0 invalid objects")
NETGATE | Passsed | Failed
1. Backup the NegGateConfig.ini and moddcm.rpt
2. Uninstall Netgate from Add/Remove Programs
3. Install Netagte 30113 BN2
4. Reconfigure and make sure service is started
5. Repeat the step 1~4 on each Netgate server
ARCHIVE MANAGER / BACKUP MANAGER | Passed | Failed
1. Backup the archman and backman configuration file
2. Uninstall Archive manager and backup manager
3. Install Archive manager 30113 BN1 and Backup manager 30113 BN1
4. Reconfigure and make sure service is started
MEDIA SERVER | Passed | Failed
1. Backup configuration and lable file
2. Uninstall Media server
3. Install Media server 30113 BN4
4. Reconfigure and make sure service is started
Admin Web page | Value
| Before | After
1. System
2-1. Profile - [Audit]
ENABLE_AUDIT_TRAIL
2-2. Profile - [Compatible]
FULL_TEXT_SEARCH
USE_V4_SCHEMA
2-3. Profile - [Dictation]
ENCODING_MP3
EXTERNAL_DICTATE
EXTERNAL_HOST
EXTERNAL_HOSTNAME
HOSTNAME
PASSWORD
PROTOCOL
SHARENAME
USERNAME
2-4. Profile - [Netgate]
BACKUP_B1
ENABLE_CREATE_ICOM_IMAGE
PUBLIC_ERROR_PATHNAME
PUBLIC_SPOOL_PATHNAME
SHARE_FOLDER_PASSWORD
SHARE_FOLDER_USERNAME
USE_DISTRIBUTED_SERVER
USE_FORCE_OVERWRITE
2-5. Profile - [Orthoview]
ENABLE
HOSTNAME
PASSWORD
PROTOCOL
SHARENAME
TIMEOUT
USERNAME
2-6. Profile - [Patient]
ID_DELIMITER
2-7. Profile - [Report]
ORDERED_ONLY
2-8. Profile - [Ruleset]
USE_ACCESSRULE
USE_CONVERTRULE
USE_HIDINGRULE
USE_PREFETCHRULE
USE_ROUTERULE
USE_VERIFYRULE
2-9. Profile - [Server]
EXTERNAL_LICENSE_SERVER
EXTERNAL_WDO_SERVER
EXTERNAL_WEBPUSH_SERVER
EXTERNAL_WEB_FILE_SERVER
LICENSE_SERVER
WDO_SERVER
WEBPUSH_SERVER
WEB_FILE_SERVER
INTERNAL_IP_FILTER
2-10. Profile - [Storage]
ENABLE_CACHE_ICON
MEDIABURN_OVERSIZE_LIMIT
MEDIABURN_OVERSIZE_WARNING
MEDIABURN_OVERSIZE_WEIGHT
USE_JPEG2K_COMPRESSION
USE_MEDIA_SERVER
2-11. Profile - [User]
USER_DEFINED_READDOC
USER_DEFINED_REFDOC
2-10. Profile - [Validate]
MATCH_AVAILABLE_DATE
ENABLE_STANDALONE_PACS
ENABLE_STANDALONE_RIS
USE_AUTOMATCH_RULE3
UNMATCH_AVAILABLE_STATUS
2-11. Profile - [Worklist]
HIDE_ID_ISSUER
NUM_PERPAGE
USE_DEMO_FOLDER : F
USE_REMOTE_COLLABORATION : F
Final Testing | Passed | Failed
1. Start All Server modules
2. Send bunch of studies to Netgate
3. Check Netgate log and Error folder
4. Login as admin and superadmin
5. Install WebView folder
6. Install Viewer folder
7. Open a study
8. Close a study
9. Test local burning or Media server
10. Check the HL7 interface
11. Check the Modality worklist