## New Installation
PACS服务器安装实施路径
医院名称 | 实施人员 | 审核确认
操作系统设置 | Passed | Failed
1. Windows 激活
2. Windows 升级
3. Windows 防火墙关闭
4. 关闭EP. /noexecute=AlwaysOff in boot.ini
5. 性能选项改为最佳性能
6. 处理器计划改为“后台服务”
7. 虚拟内存修改为 '自动管理所有驱动器的分页大小'
8. 关闭WINDOWS Error reporting服务
9. 取消系统失败后自动重启选项
10. 开启写入转存文件
11. spectra/spclient用户建立
12. spetra设置为administrator组
常用工具 | Passsed | Failed
1. 杀毒软件已安装（医院如有和医院确认）
2. 安装常用输入法
3. WINRAR压缩工具
4. 远程工具TEAMVIEWER/RADMIN/VNC/MSTSC
Oracle设置 | Passed | Failed
1. 如是是10g请确认打上最新的 10.2.0.4 补丁
2. 确认 listener.ora 监听文件
3. 确认 tnsname.ora 文件
4. 是否有做定时EXP导出
5.Process和Session是否设置
IIS 安装 | Passed | Failed
1.应用程序开发
1-1. ASP.NET
1-2. .NET 扩展性
1-3. ASP
1-4. CGI
1-5. ISAPI 扩展
1-6. ISAPI 筛选器
1-7. 在服务器端的包含文件
2. Security
2-1.基本用户验证
2-2. Windows 身份用户验证
3. Management Tools
3-1. IIS 管理控制台
3-2. IIS 管理脚本及工具
3-3.管理服务
3-4. IIS 6 管理兼容性
3-4-1. IIS 6 元数据库兼容性
3-4-2. IIS 6 WMI 兼容性
3-4-3. IIS 6 脚本工具
3-4-4. IIS 6 管理控制台
4. FTP服务器
4-1. FTP Server
4-2. FTP 扩展
5. .NET Framework Version 1.1安装
5-1. .NET Framework 1.1 Service Pack 1安装
5-2. .NET Framework 1.1 Service Pack 1 ASP.NET 安全更新
6. iewebcontrol.msi
IIS配置 | Passed | Failed
1. 允许 ASP.NET v1.1.4332 ISAPI and CGI 执行扩展路径
2. 新增 MIME支持类型 ARC, DCM, DIC, MP3
3. 应用程序池允许32位模式
4. 设置默认应用程序池为 ASP.NET 1.1
5. 将VOLUME增加至虚拟目录
INFINITT Admin 安装 | Value
1. 医院LOGO
2. G3服务器地址
3. 设置License
4.安装 WebView
Internet Security | Passed | Failed
1. 关闭 IE ESC
2. 设置IE的Internet Options
2-1. 修改安全级别，添加ActiviX控件许可
2-2. 将IP加入至信任站点
Admin Web page | Passed | Failed
1. Basic Code
1-1 创建 Institution code（注意和Institution Name一致）
1-2 Station里注册NETGATE等站点（注意备注连接的设备）
2. System
2-1. Profile - [Audit]
ENABLE_AUDIT_TRAIL : T 根据医院需求是否开启审计
2-2. Profile - [Compatible]
FULL_TEXT_SEARCH : F 关闭全文件搜索
关闭 USE_V4_SCHEMA : F
2-3. Profile - [Netgate]
BACKUP_B1 : F 关闭B1
2-4. Profile - [Storage]
USE_J2K_COMPRESSION : T 开启JPEG2000压缩
2-5. User Defined UI Defaults 配置用户挂片协议及权限
3. User
3-1. 新增用户
3-2. 设置用户在License Server中的权限
最终测试 | Passed | Failed
1. Negate 服务能起来
2. 可以往 Netgate发送图像
3. 注意Netgate的Log,Error,Spool路径下的磁盘容量最好够
4. 以admin登陆PACS
5. 安装 WebView和VIEWER
6. 新建测试账号
7. 打开病人图像
8.PACSPush是否已安装并修改配置
9.Broker是否已安装可以登记至PACS并修改病人状态
10.WORKGATE可以正常让设备获取工作列表
11.服务自动重启服务是否已安装
12.Archive图像压缩是否已设置
13.设备WORKLIST获取是否正常，是否已设置独立视图
14.是否已做数据库定时备份
15.紧急预案是否已做并交给信息科
16.用户基本挂片协议是否已设置，PACS显示时间应为Acqision Time
17.图像匹配工具AcqManager是否已培训
18.图像备份模块Backup是否已安装并配置
19.记录所有服务器信息

## Upgrade (hidden)
Check List for the Upgarde
Hospital Name | Upgrader | Approver
SPECTRA DATABASE | Value
1. Current version of spectra databse
2. New version
From 3090 to 30113 | Passed | Failed
ALTER TABLE LICENSESESSION DROP CONSTRAINT LICENSESSION_SESSION_TYPE_CK;
ALTER TABLE STUDYICON DROP CONSTRAINT STUDY_ICON_LOB_NN;
DELETE LICENSESESSION;
COMMIT;
@Patch_3090-3091.sql
@Patch_3091-30101.sql
@Patch_30101-30102.sql
@Patch_30102-30110.sql
@Patch_30110-30111.sql
@Patch_30111-30112.sql
@Patch_30112-30113.sql
@Spectrarebuild.sql
@Pkgmedia.sql
@Pbdmedia.sql
SELECT OBJECT_NAME FROM USER_OBJECTS WHERE STATUS != 'VALID'; (The result must be the "Found 0 invalid objects")
NETGATE | Passsed | Failed
1. Backup the NegGateConfig.ini and moddcm.rpt
2. Uninstall Netgate from Add/Remove Programs
3. Install Netagte 30113 BN2
4. Reconfigure and make sure service is started
5. Repeat the step 1~4 on each Netgate server
ARCHIVE MANAGER / BACKUP MANAGER | Passed | Failed
1. Backup the archman and backman configuration file
2. Uninstall Archive manager and backup manager
3. Install Archive manager 30113 BN1 and Backup manager 30113 BN1
4. Reconfigure and make sure service is started
MEDIA SERVER | Passed | Failed
1. Backup configuration and lable file
2. Uninstall Media server
3. Install Media server 30113 BN4
4. Reconfigure and make sure service is started
Admin Web page | Value
| Before | After
1. System
2-1. Profile - [Audit]
ENABLE_AUDIT_TRAIL
2-2. Profile - [Compatible]
FULL_TEXT_SEARCH
USE_V4_SCHEMA
2-3. Profile - [Dictation]
ENCODING_MP3
EXTERNAL_DICTATE
EXTERNAL_HOST
EXTERNAL_HOSTNAME
HOSTNAME
PASSWORD
PROTOCOL
SHARENAME
USERNAME
2-4. Profile - [Netgate]
BACKUP_B1
ENABLE_CREATE_ICOM_IMAGE
PUBLIC_ERROR_PATHNAME
PUBLIC_SPOOL_PATHNAME
SHARE_FOLDER_PASSWORD
SHARE_FOLDER_USERNAME
USE_DISTRIBUTED_SERVER
USE_FORCE_OVERWRITE
2-5. Profile - [Orthoview]
ENABLE
HOSTNAME
PASSWORD
PROTOCOL
SHARENAME
TIMEOUT
USERNAME
2-6. Profile - [Patient]
ID_DELIMITER
2-7. Profile - [Report]
ORDERED_ONLY
2-8. Profile - [Ruleset]
USE_ACCESSRULE
USE_CONVERTRULE
USE_HIDINGRULE
USE_PREFETCHRULE
USE_ROUTERULE
USE_VERIFYRULE
2-9. Profile - [Server]
EXTERNAL_LICENSE_SERVER
EXTERNAL_WDO_SERVER
EXTERNAL_WEBPUSH_SERVER
EXTERNAL_WEB_FILE_SERVER
LICENSE_SERVER
WDO_SERVER
WEBPUSH_SERVER
WEB_FILE_SERVER
INTERNAL_IP_FILTER
2-10. Profile - [Storage]
ENABLE_CACHE_ICON
MEDIABURN_OVERSIZE_LIMIT
MEDIABURN_OVERSIZE_WARNING
MEDIABURN_OVERSIZE_WEIGHT
USE_JPEG2K_COMPRESSION
USE_MEDIA_SERVER
2-11. Profile - [User]
USER_DEFINED_READDOC
USER_DEFINED_REFDOC
2-10. Profile - [Validate]
MATCH_AVAILABLE_DATE
ENABLE_STANDALONE_PACS
ENABLE_STANDALONE_RIS
USE_AUTOMATCH_RULE3
UNMATCH_AVAILABLE_STATUS
2-11. Profile - [Worklist]
HIDE_ID_ISSUER
NUM_PERPAGE
USE_DEMO_FOLDER : F
USE_REMOTE_COLLABORATION : F
Final Testing | Passed | Failed
1. Start All Server modules
2. Send bunch of studies to Netgate
3. Check Netgate log and Error folder
4. Login as admin and superadmin
5. Install WebView folder
6. Install Viewer folder
7. Open a study
8. Close a study
9. Test local burning or Media server
10. Check the HL7 interface
11. Check the Modality worklist